## Sheet1
Task | Start Date | End Date | Week | Days | Person | Depends
Create Plastic Enclosure Requirements | 2014-09-11 | 2014-09-16 | 1 | 5 | Dave
Design NAND Gate circuit | 2014-09-15 | 2014-09-17 | 1 | 2 | Ryan
Initalize Code for PIC | 2014-09-18 | 2014-09-18 | 1 |  | Dave
Finalize schedule | 2014-09-16 | 2014-09-18 | 1 | 2 | Ryan
Design NOR Gate Block circuit | 2014-09-18 | 2014-09-20 | 1 | 2 | Ryan
Meet with senior plastics students | 2014-09-18 | 2014-09-19 | 1 | 1 | Ryan, Dave
Design AND Gate Block circuit | 2014-09-18 | 2014-09-20 | 1 | 2 | Ryan
Design NOT Gate circuit | 2014-09-20 | 2014-09-22 | 2 | 2 | Ryan
Prototype NAND Gate circuit | 2014-09-22 | 2014-09-24 | 2 | 2 | Ryan
Finalize Power Management Circuit | 2014-09-22 | 2014-09-22 | 2 |  | Steve
Write Technical Requirements | 2014-09-21 | 2014-09-22 | 2 | 1 | Dave
Finish PCB layout of Buffer gate | 2014-09-21 | 2014-09-23 | 2 | 2 | Ryan
Order Parts for power management circuit | 2014-09-24 | 2014-09-24 | 2 |  | Steve
Design OR Gate Block circuit | 2014-09-22 | 2014-09-24 | 2 | 2 | Ryan
Design Buffer Gate Block circuit | 2014-09-24 | 2014-09-26 | 2 | 2 | Ryan
Order PIC | 2014-09-25 | 2014-09-25 | 2 |  | Dave
Prototype NOR Gate circuit | 2014-09-23 | 2014-09-25 | 2 | 2 | Ryan
Write code to output logic signals | 2014-09-26 | 2014-09-26 | 2 |  | Dave
Start PCB layout of power management circuit | 2014-09-26 | 2014-09-26 | 2 |  | Steve
Prototype OR Gate circuit | 2014-09-24 | 2014-09-26 | 2 | 2 | Ryan
Prototype AND Gate circuit | 2014-09-26 | 2014-09-28 | 2 | 2 | Ryan
Prototype Buffer Gate circuit | 2014-09-28 | 2014-09-30 | 3 | 2 | Ryan
Prototype NOT Gate circuit | 2014-09-30 | 2014-10-02 | 3 | 2 | Ryan
Write state machine | 2014-09-29 | 2014-09-29 | 3 |  | Dave
Start PCB layout of NAND gate circuit | 2014-09-27 | 2014-09-29 | 3 | 2 | Ryan
Prototype OR Gate circuit | 2014-09-29 | 2014-10-01 | 3 | 2 | Ryan
Choose battery | 2014-09-30 | 2014-10-01 | 3 | 1 | Steve
Start PCB layout of NOR gate circuit | 2014-09-30 | 2014-10-02 | 3 | 2 | Ryan
Start PCB layout of OR gate circuit | 2014-10-02 | 2014-10-04 | 3 | 2 | Ryan
Start PCB layout of NOT gate circuit | 2014-10-04 | 2014-10-06 | 4 | 2 | Ryan
Handle Inputs from buttons | 2014-10-08 | 2014-10-08 | 4 |  | Dave
Finish PCB layout of AND gate | 2014-10-06 | 2014-10-08 | 4 | 2 | Ryan
Start PCB layout of Buffer gate circuit | 2014-10-08 | 2014-10-10 | 4 | 2 | Ryan
Finish PCB layout of OR gate | 2014-10-10 | 2014-10-12 | 4 | 2 | Ryan
Start PCB layout of AND gate circuit | 2014-10-12 | 2014-10-14 | 5 | 2 | Ryan
Spec out 555 timers (for return signal) | 2014-10-10 | 2014-10-12 | 4 | 2 | Ryan
Finish PCB layout of NAND gate | 2014-10-12 | 2014-10-14 | 5 | 2 | Ryan
Drive output signals from start block | 2014-10-14 | 2014-10-14 | 5 |  | Dave
Spec out Mux (for return signal) | 2014-10-12 | 2014-10-14 | 5 | 2 | Ryan
Finish PCB layout of NOR gate | 2014-10-14 | 2014-10-16 | 5 | 2 | Ryan
Order Clamping diodes for ESD | 2014-10-16 | 2014-10-18 | 5 | 2 | Ryan
Finish PCB layout of NOT gate | 2014-10-18 | 2014-10-20 | 6 | 2 | Ryan
Order general components (Res, Cap, etc) | 2014-10-20 | 2014-10-22 | 6 | 2 | Ryan
Spec out block connections | 2014-10-22 | 2014-10-24 | 6 | 2 | Ryan
Setup test harness | 2014-10-21 | 2014-10-21 | 6 |  | Dave
Order block connectors | 2014-10-19 | 2014-10-21 | 6 | 2 | Ryan
Framing puzzle to display on screen | 2014-10-24 | 2014-10-24 | 6 |  | Dave
Design return signal circuit | 2014-10-22 | 2014-10-24 | 6 | 2 | Ryan
Prototype return signal circuit | 2014-10-24 | 2014-10-26 | 6 | 2 | Ryan
Handle return signal from end block | 2014-10-31 | 2014-10-31 | 7 |  | Dave
USB communications | 2014-11-07 | 2014-11-07 | 8 |  | Dave
Storing puzzle in eeprom | 2014-11-12 | 2014-11-12 | 9 |  | Dave
Write code to output to LCD | 2014-11-19 | 2014-11-19 | 10 |  | Dave
Sleep cycle to save battery | 2014-11-24 | 2014-11-24 | 11 |  | Dave
Puzzle parsing code | 2014-12-01 | 2014-12-01 | 12 |  | Dave
Download puzzle from pc | 2014-12-08 | 2014-12-08 | 13 |  | Dave
Write initial LCD code | 0 |  | -36 |  | Dave
Prototype power management circuit | 0 |  | -36 |  | Steve
Check noise level in power circuit | 0 |  | -36 |  | Steve
Check failure points for power circuit | 0 |  | -36 |  | Steve
Order LCD display | 0 |  | -36 |  | Dave
Order Battery | 0 |  | -36 |  | Steve
Formulas:
Start Date = Table1[[#This Row],[End Date]] - Table1[[#This Row],[Days]]
Week = WEEKNUM(Table1[[#This Row],[End Date]],2) - 37
End Date = [End Date, row above]+[Days, row above]